## Slide 1
Ethiopian Education Network to Support Agricultural Transformation (EENSAT)
<EENSAT meeting>, <12/10/2023>, <Langezijds>
PhD progress report: Crop phenology monitoring and yield estimation in fragmented agricultural landscape: A multi-sensor data fusion approach
Biniam Sisheber
Supervisor: Prof. Andy Nelson
Co-supervisor: Michael Marshall (PhD)
Co-supervisor: Daniel Ayalew (PhD)

## Slide 2: Contents
Current status
Remaining tasks to be completed
Timeline

## Slide 3: Current status
  Article II
Publications:
  Article I

## Slide 4: Current status
Manuscript III: Reviewed
Manuscript IV: To be submitted
TGS:
  28 ECTS collected and the remaining ECTS in progress
Remaining tasks:
  Revision of manuscripts
  Thesis write-up

## Slide 5: Timeline and return to Ethiopia
Activities | October |  |  |  | November |  |  |  | December |  |  |  | January to…
 |  |  | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 
Fourth manuscript submission |  |  |  |  |  |  |  |  |  |  |  |  | 
Review response and revision |  |  |  |  |  |  |  |  |  |  |  |  | 
PhD thesis write-up |  |  |  |  |  |  |  |  |  |  |  |  | 
Thesis submission |  |  |  |  |  |  |  |  |  |  |  |  | 
Preparation for defence |  |  |  |  |  |  |  |  |  |  |  |  | 
Return to Ethiopia: 24, January, 2024

## Slide 6: Thank You!