## Slide 1
Integration of a wireless sensor network and a participatory soil monitoring system for smallholder agriculture: SDI for agriculture
Progress report
Phd candidate: Amsale Zelalem, GIP, Addis Ababa University
Supervisor (s): Dr. ir. Rolf A. de By, Dr. Javier Morales Guarin, Dr. Yaregal Assabie

## Slide 2: Objective
Design and implement a (near) real-time, robust, usable, rapidly deployable and affordable soil data collection and analysis tool to assist agricultural decision makings
    Deployment of IoT-WSN for soil physical properties monitoring
    Citizen science for soil chemical properties monitoring
    Build a spatial data infrastructure (SDI)
    Develop agricultural decision support system (AgDSS)

## Slide 3: Progress
Developed IoT-WSN architecture for soil monitoring in smallholder agriculture
  Farm-level soil moisture and temperature data collected since end of 2019
Designed framework for integration of citizen science and commercial soil test kits
  Experimental farm-level soil NPK data collected, 2020 and 2023
Designed and developed data schema/model for integration of heterogeneous inputs

## Slide 4: Current status
Technical
  Completed in-situ data cleaning and pre-processing
  Completed data migration into PostGres based data schema
  Currently working on developing the decision support system
Writing
  1 journal publication (Sensors )
  1 conference presentation and publication (ICEOGI 23, Algiers; IEEE); won best paper award
  Manual prepared on IoT-WSN configuration
  Citizen science finding written but not published, yet
  Decision support system writing not completed
  Thesis: skeleton defined
ECTS: completed

## Slide 5: Challenges
Political instability
Severe data loss
  Devices stolen, damaged
  Communication, power, transport interruptions
  Safety concerns to travel
  Non-existence/scarcity of alternative data sources
Vague expectations/requirements
Work load

## Slide 6: Plan
November 2023-May 2024
  Hope to submit second and third papers for publication
  Model and deploy decision support system
  Draft findings of the decision support system
  Start working on the thesis body
June-October 2024
  Complete thesis write up and other requirements

## Slide 7
Thank you